## Sheet1
MileStone Review
Milestones | Expected Done by Date | actual done by date | Reasons Why it was not completed on time (if any)
SPMP and Requirements | 2020-10-16 | 2020-11-20 | was done by Oct 16 except for fixing things based on customer feedback
API | 2020-11-09 | TBD | I have gotten caught up in other projects and classes and haven't been able to spare the time for this
Hosting | 2020-11-23 | On track to be done on time
Frontend | 2020-11-27 | On track to be done on time
Testing | 2020-11-27 | On track to be done on time
Prototype | 2020-11-30 | TBA
Project Close | 2020-11-30 | TBA